## Original
Project Phase | Hours | Cost
Design | 25 | 1000
Design | 20 | 800
Checkins/Feedback | 5 | 200
Phase 1 (Up and Running) | 19 | 760
Setup | 7 | 280
Home | 5 | 200
About | 7 | 280
Phase 2 (Initial Site) | 15 | 600
Spring Series | 5 | 200
Conference | 3 | 120
Get Involved | 7 | 280
Phase 3 (Final Site) | 25 | 1000
Update Presenters/Sponsors | 2 | 80
Schedule | 7 | 280
Backend | 16 | 640
Hourly Rate: |  | 40
Total: | 84 | 3360

## No Design
Project Phase | Hours | Cost
Design | 5 | 200
Design | 0 | 0
Checkins/Feedback | 5 | 200
Phase 1 (Up and Running) | 19 | 760
Setup | 7 | 280
Home | 5 | 200
About | 7 | 280
Phase 2 (Initial Site) | 15 | 600
Spring Series | 5 | 200
Conference | 3 | 120
Get Involved | 7 | 280
Phase 3 (Final Site) | 25 | 1000
Update Presenters/Sponsors | 2 | 80
Schedule | 7 | 280
Backend | 16 | 640
Hourly Rate: |  | 40
Total: | 64 | 2560

## No Backend
Project Phase | Hours | Cost
Design | 5 | 200
Design | 0 | 0
Checkins/Feedback | 5 | 200
Phase 1 (Up and Running) | 19 | 760
Setup | 7 | 280
Home | 5 | 200
About | 7 | 280
Phase 2 (Initial Site) | 15 | 600
Spring Series | 5 | 200
Conference | 3 | 120
Get Involved | 7 | 280
Phase 3 (Final Site) | 12 | 480
Update Presenters/Sponsors | 2 | 80
Schedule | 10 | 400
Backend | 0 | 0
Hourly Rate: |  | 40
Total: | 51 | 2040